## Cover (hidden)
Fish Feeder 2026 Readiness Tracker
Project governance, readiness progress and execution status
CONTENTS | PURPOSE
Dashboard | Executive view of overall progress, stage completion and priority actions
Project Team | Department owners for the Fish Feeder program
FF_2026 | Detailed part-level readiness tracker and milestone dates
RACI Matrix | Responsibility and accountability by readiness stage
Timeline | Program stage targets, dependencies and schedule status

## Dashboard
Fish Feeder 2026 — Readiness Dashboard
Live view from FF_2026 • Updated 06-Oct-2026 17:35
OVERALL PROGRESS |  |  | TRACKED PARTS | MECH PARTS | HW PARTS | PARTS WITH DELAY | NEXT SOURCING TARGET
19.97% |  |  | 106 | 82 | 24 | 4 | 2026-09-15
STORY IN BRIEF
Overall gate progress is 20% across 106 tracked parts. Design and part qualification are complete; sourcing is at 16%. Supplier qualification, sample procurement and factory handover remain at 0%, making downstream execution the critical path. 4 parts currently show a positive design or qualification delay.
READINESS STAGE PROGRESS
Readiness Stage | Completed | Total | Progress
Design Readiness | 91 | 106 | 85.85%
Part Qualification | 19 | 106 | 17.92%
Sourcing Readiness | 17 | 106 | 16.04%
Supplier Qualification | 0 | 106 | 0%
Sample / Lot Procurement | 0 | 106 | 0%
Factory Handover | 0 | 106 | 0%
PARTS BY FUNCTION & CATEGORY — MATURITY PROGRESS
Group | ≥90% Maturity | Total | Progress
ALL PARTS | 92 | 106 | 86.79%
New - Critical | 20 | 34 | 58.82%
New - Regular | 0 | 0 | 0%
Carryover - Critical | 9 | 9 | 100%
Carryover - Regular | 63 | 63 | 100%
Not Specified | 0 | 0 | 0%
MECH | 78 | 82 | 95.12%
New - Critical | 19 | 23 | 82.61%
New - Regular | 0 | 0 | 0%
Carryover - Critical | 7 | 7 | 100%
Carryover - Regular | 52 | 52 | 100%
Not Specified | 0 | 0 | 0%
HW | 14 | 24 | 58.33%
New - Critical | 1 | 11 | 9.091%
New - Regular | 0 | 0 | 0%
Carryover - Critical | 2 | 2 | 100%
Carryover - Regular | 11 | 11 | 100%
Not Specified | 0 | 0 | 0%
FUNCTION NOT SPECIFIED | 0 | 0 | 0%
PRIORITY ACTIONS
Priority | Action
1 — New Critical | New part with high complexity, longer sourcing lead time, higher qualification requirements, or other critical factors.
2 — New Regular | New part with lower complexity, shorter sourcing lead time, and relatively straightforward qualification requirements.
3 — Carryover Critical | Existing/carryover part with high complexity, longer sourcing lead time, higher qualification requirements, or other critical factors.
4 — Carryover Regular | Existing/carryover part with lower complexity, shorter sourcing lead time, and relatively straightforward qualification requirements.

## Project Team
Department | Fish Feeder
Product Engineering | Mallesha
Design | Ravindra Namburi
HW | Pavan K
FW | Prem
Procurement | Ravindra Kolla
Quality | Jeyamurgan
Production | Venu
Customer Success | Pavan N
V&V | Kiran

## FF_2026_Ref_Backup (hidden)
Design Readiness | [14 empty] | Part Qualification Readiness | [6 empty] | Sourcing Readiness | [13 empty] | Supplier Qualification |  |  |  |  | Sample / Lot Procurement |  |  |  |  | Factory Handover Rediness
Sl.No | PE Kick-off Date | Part Number | Part Discription | Part Type | Part Category | Part Function | BOM Rev. No | Rev. No | Qty | Design Readiness Planned | Design Readiness Actual | Maturity % | Doc. Rec'd | Status (Days) | PE Verif. Planned | PE Verif. Actual | Status (Days) | Ready for PQ | Drawing / Spec to SCM | Sourcing Target Date | Comments/ Remarks | Drawing / Spec to Vendors | Vendors Identification Planned | Vendors Identification Actual | RFQ released | Technical queries closure | Quotations received | Vendor Finalization ((ToCo,) | Sample size | Lead Time Type | Lead time confirmation Planned | Lead time confirmation Actual | Release of PO | Status (Days) | Remarks/ Comments | Vendor visit Required | PPAP/FAI (if applicable) | Sample approval | Quality & MF agreements | Remarks/ Comments | Samplet dispatch | Sample receipt | QA (CFT) | Distpacth Sample to Design | Remarks/ Comments | Check Form & Fit | Testing | Open Issues | Design Changes | BOM revision updates | Part Qualification Required | Part Approval | Remarks/ Comments
1 | 2026-07-07 | TBA | H- Plate | New | New - Regular | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-10 |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  | 26th for approval submission
2 | 2026-07-07 | TBA | Vertical Doser & Dispenser Structure | New | New - Critical | Mech | 0 | A | 1 | 2026-07-08 | 2026-07-30 | 90% | Yes | 16 | 2026-07-30 | 2026-07-30 | 0 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-10 |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01
3 | 2026-07-07 | TBA | Vertical Doser top plate | New | New - Regular | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-10 |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01
4 | 2026-07-07 | TBA | Vertical Doser bottom plate | New | New - Regular | Mech | 0 | A | 1 | 2026-07-08 | 2026-07-30 | 90% | Yes | 16 | 2026-07-30 | 2026-07-30 | 0 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-10 |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01
5 | 2026-07-07 | TBA | Vertical doser Side Support | New | New - Regular | Mech | 0 |  | 2 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-10 |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01
6 | 2026-07-07 | TBA | Doser case | New | New - Regular | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Low | 2026-09-11 |  | 2026-09-01 |  |  | 2026-09-21 |  |  |  | Visit Plan: 21–23 Sep; Tool Dev. Reports: Ravindra Namburi to provide.
7 | 2026-07-07 | TBA | Doser motor holder | New | New - Critical | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
8 | 2026-07-07 | TBA | Vertical doser wheel assembly | New | New - Critical | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
9 | 2026-07-07 | TBA | Doser wheel insert | New | New - Critical | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-20 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
10 | 2026-07-07 | TBA | Doser wheel | New | New - Critical | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
11 | 2026-07-07 | TBA | Doser Wing nut | New | New - Critical | Mech | 0 |  | 6 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
12 | 2026-07-07 | TBA | Feed reducer | New | New - Critical | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
13 | 2026-07-07 | TBA | Motor Protector | New | New - Regular | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-06-23 |  | 2026-08-04 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Medium | 2026-10-02 |  | 2026-09-01 |  |  | 2026-09-21
14 | 2026-07-07 | TBA | Dosel wheel bearing | New | New - Critical | Mech | 0 |  | 2 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | What is the warranty period confirmed by the selected supplier? - 24 months from manufacturing or 12 months from the date of installation whichever is the earlier. | 2026-08-03 | 2026-08-10 |  | 2026-08-05 | 2026-08-17 | 2026-08-17 | 2026-08-28 | 10 | Low | 2026-09-11 |  | 2026-09-01
15 | 2026-07-07 | TBA | Vertical doser Motor | New | New - Critical | HW | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 80% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | No | 2026-07-31 | 2026-09-15 | 24th Aug- Vendor discussion Open Points 1.Shaft to be changed to rust-proof material. 2.XT30 or XT60 connector with open-ended wire (male/female as required) 3.2 yrs warranty As of now information: 6 months 2nd Sep - 2026 For Model: RMCS-1211 – Industrial Grade IG45 Planetary DC Geared Motor, 50W, 10RPM, 12V, 186Kgcm, we have the following three options available: Option Construction 1 Electro-plated DC motor case + Stainless Steel gearbox case + Stainless Steel 304 gearbox shaft 2 Electro-plated DC motor case + Zinc-Nickel alloy plated gearbox case + Stainless Steel 304 gearbox shaft 3 Electro-plated DC motor case + Stainless Steel 304 gearbox shaft The above options differ mainly in the gearbox case material and construction. For complete technical specifications, please refer to the datasheet: https://download.robokits.co.in/downloads/rmcs_1211_datasheet_01.pdf Waiting for samples - 5 numbers | 2026-08-03 | 2026-08-10 |  | 2026-08-04 |  |  |  | 10 | High | 2026-10-23
16 | 2026-07-07 | TBA | Vertical doser feed stopper | New | New - Regular | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 |  |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Low | 2026-09-11 |  | 2026-09-01
17 | 2026-07-07 | TBA | Feed Dispenser - (DISC) | New | New - Critical | Mech | 0 | B | 1 | 2026-07-08 | 2026-07-30 | 90% | Yes | 16 | 2026-07-30 | 2026-07-30 | 0 | Yes | 2026-07-31 | 2026-09-15 | 6th Aug: Query from SCM: Feed dispenser – pipe details & source details of the product developed. 7th Aug: We will confirm the results of the thickness variation and power consumption tests on Monday. 12th Aug: Today rework will complete and Tomorrow test will be finished. 13th Aug: 14th Aug 2026 - will get details from design team 18th-Aug-2026: Received updated drawing and pipe details. MOQ: 40 tubes/pipes - 1800-2000 no's - supplier under working Note: If the XT30/XT60 -> The IP may fail. Pavan, could you please look into it once? | 2026-08-03 |  |  | 2026-08-04 | 2026-08-18 |  |  | 10 | High | 2026-10-23
18 | 2026-07-07 | TBA | 12V Dispenser motor | New | New - Critical | HW | 0 | A | 1 | 2026-07-08 | 2026-08-05 | 90% | Yes | 20 | 2026-07-30 | 2026-08-06 | 5 | Yes | 2026-07-31 | 2026-09-15 | HW Comments (30th July 2026): Motor procurement can start. Any cable modification can be carried out by a harness vendor. Timeline: Drawing will be ready by 4th Aug. Motor and cable. Along with an assembly drawing. Get the warrenty details | 2026-08-03 | 2026-08-10 |  | 2026-08-13 |  |  |  | 10 | High | 2026-10-23 |  |  |  | 1. Specification change may require new PN, setup, MOQ, and price revision. 2. Wire colours differ from their standard; Blue + Red combination can be provided for samples. 3. New shaft material has longer lead time, so sample timeline is not yet confirmed. 4. Current PN 10213 pricing is based on bulk availability. 5. Vendor needs MOQ and ordering schedule to proceed. 6. Stock available? - 20 No's
19 | 2026-07-07 | TBA | Dispenser Motor holder | New | New - Regular | Mech | 0 |  | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-10 |  | 2026-08-04 | 2026-08-07 | 2026-08-07 | 2026-08-28 | 10 | Low | 2026-09-11 |  | 2026-09-01
XT-60 Male Connector
Relay PCB
Cable from PCB doser connector to relay PCB
Inter connect cable from Relay PCB to PM PCB
Formulas:
Status (Days) = IF(OR([Design Readiness Planned]="",[Design Readiness Actual]=""),"",SIGN([Design Readiness Actual]-[Design Readiness Planned])*(NETWORKDAYS(MIN([Design Readiness Planned],[Design Readiness Actual]),MAX([Design Readiness Planned],[Design Readiness Actual]))-1))
Status (Days) = IF(OR([Part Qualification Readiness]="",[PE Verif. Actual]=""),"",SIGN([PE Verif. Actual]-[Part Qualification Readiness])*(NETWORKDAYS(MIN([Part Qualification Readiness],[PE Verif. Actual]),MAX([Part Qualification Readiness],[PE Verif. Actual]))-1))
Lead time confirmation Planned = IF(OR([Drawing / Spec to SCM]="",[Lead Time Type]=""),"",WORKDAY([Drawing / Spec to SCM],IF([Lead Time Type]="Low",30,IF([Lead Time Type]="Medium",45,IF([Lead Time Type]="High",60,"")))))

## FF_2026
Design Readiness | [15 empty] | Part Qualification Readiness | [6 empty] | Sourcing Readiness | [14 empty] | Supplier Qualification |  |  |  |  | Sample / Lot Procurement |  |  |  |  | Factory Handover Rediness
Sl.No | PE Kick-off Date | Part Number | Part Discription | Part Type | Scope | Part Category | Part Function | BOM Rev. No | Draw. Rev. No | Qty | Design Readiness Planned | Design Readiness Actual | Maturity % | Doc. Rec'd | Status (Days) | PE Verif. Planned | PE Verif. Actual | Status (Days) | Ready for PQ | Drawing / Spec to SCM | Sourcing Target Date | Comments/ Remarks | Drawing / Spec to Vendors | RFQ released | Vendors Identification Planned | Technical queries closure | Vendors Identification Actual | Quotations received | Vendor Finalization ((ToCo,) | Shortlisted Supplier Name | Sample size | Release of PO | Lead Time Type | Lead time confirmation Planned | Lead time confirmation Actual | Status (Days) | Remarks/ Comments | Vendor visit Required | PPAP/FAI (if applicable) | Sample approval | Quality & MF agreements | Remarks/ Comments | Samplet dispatch | Sample receipt | QA (CFT) | Distpacth Sample to Design | Remarks/ Comments | Check Form & Fit | Testing | Open Issues | Design Changes | BOM revision updates | Part Qualification Required | Part Approval | Remarks/ Comments
1 | 2026-07-07 | TBA | PM125 SQ- Float Version | New | Eruvaka | New - Critical | Mech | rB |  | 1 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
2 | 2026-07-07 | ERLPM04 | SQ125 Structure Assy | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
3 | 2026-07-07 | ER790 | SQ125 Spider | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
4 | 2026-07-07 | ER791 | SQ125 Pipe | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
5 | 2026-07-07 | ER792 | SQ125 H Structure | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
6 | 2026-07-07 | ERFS072 | M8 X 55 Hex head bolt | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 20 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
7 | 2026-07-07 | ERFS018 | M8 Washer | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 50 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
8 | 2026-07-07 | ERFS020 | M8 Nut | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 28 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
9 | 2026-07-07 | ERPA018 | Strech film | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 340 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
10 | 2026-07-07 | ERPA008 | Strech film | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 100 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
11 | 2026-07-07 | ERLPM05 | SQ125 Hopper Assembly | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
12 | 2026-07-07 | ER785 | SQ125 Square Hopper | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
13 | 2026-07-07 | ER828 | Pre-Mould Eruvaka Logo | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
14 | 2026-07-07 | ER829 | Pre-Mould Eruvaka Text - Blue | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
15 | 2026-07-07 | ER830 | Pre-Mould PondMother - Blue | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
16 | 2026-07-07 | ER831 | Pre-Mould Skretting Logo - Red | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
17 | 2026-07-07 | ER789 | SQ125 Rain Cap (Red) | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
18 | 2026-07-07 | ERC092 | Teflon Tape | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
19 | 2026-07-07 | ERC071 | Desiccant Silica Gel | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
20 | 2026-07-07 | ER032 | PG11 (Gland + Lock nut+O ring) | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 6 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
21 | 2026-07-07 | TBA | H- Plate | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-07 | 2026-09-25 | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Medium | 2026-10-30 | 2026-09-25 | -25
22 | 2026-07-07 | ERFS070 | M8 Lock washer | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
23 | 2026-07-07 | ER010 | Top Lid | Carryover | Eruvaka | Carryover - Critical | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
24 | 2026-07-07 | ER014 | Knob Handle | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
25 | 2026-07-07 | ERFS007 | M4X10 Hex head bolt | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
26 | 2026-07-07 | ER490 | LID MAGNET ASSY | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
27 | 2026-07-07 | ER088 | Lid Magnet Holder | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
28 | 2026-07-07 | ER086 | Lid Magnet | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
29 | 2026-07-07 | ER085 | Lid Magnet Clamp | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
30 | 2026-07-07 | ER150 | Rivets (4mm Dia x 18mm length) | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 8 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
31 | 2026-07-07 | ER151 | Rivet Washer (ID-4.5mm OD-8mm) | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 8 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
32 | 2026-07-07 | ERFS048 | M8x100 Hex head bolt | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
33 | 2026-07-07 | ERFS050 | M8 Locknut | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
34 | 2026-07-07 | ER022 | Solar Panel 40 watt | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
35 | 2026-07-07 | ERFS017 | M6X20 Hex head bolt | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 10 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
36 | 2026-07-07 | ERFS015 | M6 Washer | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 20 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
37 | 2026-07-07 | ERFS014 | M6 Nut | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
38 | 2026-07-07 | ER786 | SQ125 Solar Panel Mounting Bracket | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
39 | 2026-07-07 | ERFS073 | M8 X 65 Hex head bolt | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
40 | 2026-07-07 | TBA | Vertical Doser and Dispencer assembly | New | Eruvaka | New - Critical | Mech | rB | 0 | 1 | 2026-07-08 |  | 95% | Yes |  |  |  |  | No | [11 empty] | 10
41 | 2026-07-07 | TBA | Vertical Doser & Dispenser Structure | New | Eruvaka | New - Critical | Mech | rA | A | 1 | 2026-07-08 | 2026-07-30 | 90% | Yes | 16 | 2026-07-30 | 2026-07-30 | 0 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Medium | 2026-10-30 | 2026-09-25 | -25
42 | 2026-07-07 | TBA | Vertical Doser top plate | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Medium | 2026-10-30 | 2026-09-25 | -25
43 | 2026-07-07 | TBA | Vertical Doser bottom plate | New | Eruvaka | New - Critical | Mech | rA | A | 1 | 2026-07-08 | 2026-07-30 | 90% | Yes | 16 | 2026-07-30 | 2026-07-30 | 0 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Medium | 2026-10-30 | 2026-09-25 | -25
44 | 2026-07-07 | TBA | Vertical doser Side Support | New | Eruvaka | New - Critical | Mech | rA | 0 | 2 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | Feedback from the Supplier - Jig/fixtures needed after samples finalisation before production they will make ready | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Medium | 2026-10-30 | 2026-09-25 | -25
45 | 2026-07-07 | ERFS065 | M4x10 CSK phillip head screw | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 6 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
46 | 2026-07-07 | TBA | Vertical Doser assembly | New | Eruvaka | New - Critical | Mech | rB | 0 | 1 | 2026-07-08 |  | 95% | Yes |  |  |  |  | No | [11 empty] | 10
47 | 2026-07-07 | TBA | Doser Motor Assembly | New | Eruvaka | New - Critical | HW | rB |  | 1 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
48 | 2026-07-07 | TBA | Vertical doser Motor | New | Eruvaka | New - Critical | HW | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 80% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | No | 2026-07-31 | 2026-09-15 | 24th Aug- Vendor discussion Open Points 1.Shaft to be changed to rust-proof material. 2.XT30 or XT60 connector with open-ended wire (male/female as required) 3.2 yrs warranty As of now information: 6 months 2nd Sep - 2026 For Model: RMCS-1211 – Industrial Grade IG45 Planetary DC Geared Motor, 50W, 10RPM, 12V, 186Kgcm, we have the following three options available: Option Construction 1 Electro-plated DC motor case + Stainless Steel gearbox case + Stainless Steel 304 gearbox shaft 2 Electro-plated DC motor case + Zinc-Nickel alloy plated gearbox case + Stainless Steel 304 gearbox shaft 3 Electro-plated DC motor case + Stainless Steel 304 gearbox shaft The above options differ mainly in the gearbox case material and construction. For complete technical specifications, please refer to the datasheet: https://download.robokits.co.in/downloads/rmcs_1211_datasheet_01.pdf Waiting for samples - 5 numbers | 2026-08-03 | 2026-08-04 | 2026-08-10 |  |  |  |  | Dazzle Robotics Pvt. Ltd. | 10 | 2026-09-18 | High |  |  |  | 1. RMCS 1211 - 5no's RFQ in process. 2. RMCS 2698 5no's PO released
49 | 2026-07-07 | TBA | FF - Doser Motor Wire Cable | New | Eruvaka | New - Critical | HW | rB | A | 1 | 2026-07-08 |  | 0% | Yes |  |  |  |  | No | [11 empty] | 10
50 | 2026-07-07 | ERFS081 | M4x16 CSK Philips head screw | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
51 | 2026-07-07 | TBA | Doser case | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21 |  |  |  | Visit Plan: 21–23 Sep; Tool Dev. Reports: Ravindra Namburi to provide.
52 | 2026-07-07 | TBA | Doser motor holder | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
53 | 2026-07-07 | TBA | Vertical doser wheel assembly | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
54 | 2026-07-07 | TBA | Doser wheel insert | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-20 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
55 | 2026-07-07 | TBA | Doser wheel | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
56 | 2026-07-07 | TBA | Doser Wing nut | New | Eruvaka | New - Critical | Mech | rA | 0 | 6 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
57 | 2026-07-07 | TBA | Feed reducer | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
58 | 2026-07-07 | TBA | Motor Protector | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-06-23 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Exousia Automotive Private Limited | 10 | 2026-09-01 | Medium | 2026-10-30 |  |  | Trails completed, samples ready and dispatch before 05th Oct | 2026-09-21
59 | 2026-07-07 | TBA | Dosel wheel bearing | New | Eruvaka | New - Critical | Mech | rA | 0 | 2 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 | What is the warranty period confirmed by the selected supplier? - 24 months from manufacturing or 12 months from the date of installation whichever is the earlier. | 2026-08-03 | 2026-08-05 | 2026-08-10 | 2026-08-17 |  | 2026-08-17 | 2026-08-28 | Pacific Bearings Pvt Ltd | 10 | 2026-09-01 | Low | 2026-10-09 | 2026-09-22 | -13
60 | 2026-07-07 | TBA | Vertical doser feed stopper | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 |  | 2026-08-07 |  | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Low | 2026-10-09 | 2026-09-25 | -10
61 | 2026-07-07 | ER481 | Hall sensor PCB | Carryover | Eruvaka | Carryover - Critical | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
62 | 2026-07-07 | ERFS025 | M3x6 Pan head phillips screw | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 2 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
63 | 2026-07-07 | ER480 | Magnets | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
64 | 2026-07-07 | TBA | Feed Dispenser | New | Eruvaka | New - Critical | Mech | rA | B | 1 | 2026-07-08 | 2026-07-30 | 90% | Yes | 16 | 2026-07-30 | 2026-07-30 | 0 | Yes | 2026-07-31 | 2026-09-15 | 6th Aug: Query from SCM: Feed dispenser – pipe details & source details of the product developed. 7th Aug: We will confirm the results of the thickness variation and power consumption tests on Monday. 12th Aug: Today rework will complete and Tomorrow test will be finished. 13th Aug: 14th Aug 2026 - will get details from design team 18th-Aug-2026: Received updated drawing and pipe details. MOQ: 40 tubes/pipes - 1800-2000 no's - supplier under working Note: If the XT30/XT60 -> The IP may fail. Pavan, could you please look into it once? | 2026-09-18 | 2026-09-19 | 2026-09-19 | [5 empty] | 10 |  | High |  |  |  | Waiting for quotation, based on new design received on 19th Sep
65 | 2026-07-07 | TBA | Dispenser Motor holder | New | Eruvaka | New - Critical | Mech | rA | 0 | 1 | 2026-07-08 | 2026-07-08 | 90% | Yes | 0 | 2026-07-30 | 2026-07-15 | -11 | Yes | 2026-07-31 | 2026-09-15 |  | 2026-08-03 | 2026-08-04 | 2026-08-10 | 2026-08-07 |  | 2026-08-07 | 2026-08-28 | G Industries | 10 | 2026-09-01 | Low | 2026-10-09 | 2026-09-25 | -10
66 | 2026-07-07 | TBA | M5 Flange nut | New | Eruvaka | New - Critical | Mech | rB |  | 1 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
67 | 2026-07-07 | TBA | 12V Dispenser motor wire assembly | New | Eruvaka | New - Critical | HW | rB | A | 1 | 2026-07-08 |  | 0% | Yes |  |  |  |  | No | [11 empty] | 10
68 | 2026-07-07 | TBA | FF - Dispenser motor cable | New | Eruvaka | New - Critical | HW | rB | A | 1 | 2026-07-08 |  | 0% | Yes |  |  |  |  | No | [11 empty] | 10
70 | 2026-07-07 | TBA | 12V Dispenser motor assembly | New | Eruvaka | New - Critical | HW | rB | A | 1 | 2026-07-08 |  | 0% | Yes |  |  |  |  | No | [11 empty] | 10
69 | 2026-07-07 | TBA | 12V Dispenser motor | New | Eruvaka | New - Critical | HW | rA | A | 1 | 2026-07-08 | 2026-08-05 | 90% | Yes | 20 | 2026-07-30 | 2026-08-06 | 5 | Yes | 2026-07-31 | 2026-09-15 | HW Comments (30th July 2026): Motor procurement can start. Any cable modification can be carried out by a harness vendor. Timeline: Drawing will be ready by 4th Aug. Motor and cable. Along with an assembly drawing. Get the warrenty details | 2026-08-03 | 2026-08-13 | 2026-08-10 | 2026-09-02 |  | 2026-09-11 | 2026-09-11 | Davies Craig | 10 | NA | High | 2026-12-04 | 2026-09-18 | -55 | 1. Specification change may require new PN, setup, MOQ, and price revision. 2. Wire colours differ from their standard; Blue + Red combination can be provided for samples. 3. New shaft material has longer lead time, so sample timeline is not yet confirmed. 4. Current PN 10213 pricing is based on bulk availability. 5. Vendor needs MOQ and ordering schedule to proceed. 6. Stock available? - 20 No's NO BUY
71 | 2026-07-07 | TBA | Lugs for Dispenser cable to PM Pcb fixing end | New | Eruvaka | New - Critical | HW | rB |  | 2 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
72 | 2026-07-07 | ERFS034 | M6 Lock nut | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 6 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
73 | 2026-07-07 | TBA | FF - Controller box Assembly | New | Eruvaka | New - Critical | Mech | rB |  | 1 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
74 | 2026-07-07 | ERFS029 | M4x10 Pan head phillips screw | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
75 | 2026-07-07 | ER365 | Controller box | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
76 | 2026-07-07 | ER3651 | Controller box Lid | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
77 | 2026-07-07 | ER3652 | Controller box Bottom | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
78 | 2026-07-07 | ER051 | Standard Membrane keypad sticker - PM125 | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
79 | 2026-07-07 | ER034 | Push button switch-Power ON/OFF | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
80 | 2026-07-07 | ER072 | 2.5mm Dia Heat Shrinkable Sleeve | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
81 | 2026-07-07 | ER070 | 2.5mm x 15cm JST cable connector (RB) | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
82 | 2026-07-07 | ET0005 | DPC-16 Silicon cover | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
83 | 2026-07-07 | ER140 | PCB mounting plate | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
84 | 2026-07-07 | ERC068 | Anabond 555 | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 0.025 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
85 | 2026-07-07 | ER500 | PM Controller PCBA V20 | Carryover | Eruvaka | Carryover - Critical | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
86 | 2026-07-07 | ERFS025 | M3 X 6 Pan head phillips screw | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
87 | 2026-07-07 | ER827 | Gromet EPDM ID 5mm | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
88 | 2026-07-07 | ER558 | IP68 Charge Controller with Wiring | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
89 | 2026-07-07 | ERFS063 | M4X16 Pan head phillips screw | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
90 | 2026-07-07 | ER582 | Cable from IP68 Charge Controller to Battery (Part-1) | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
91 | 2026-07-07 | ER581 | Power Cable from IP68 Charge Controller to PCBA | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
92 | 2026-07-07 | ER584 | Cable from IP68 Charge Controller to Solar Panel- (Part-1) | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
93 | 2026-07-07 | ER583 | Cable from IP68 Charge Controller to Battery (Part-2) | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
94 | 2026-07-07 | TBA | Relay PCB | New | Eruvaka | New - Critical | HW | rB |  | 1 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
95 | 2026-07-07 | TBA | Relay PCB and CC fixing Back plate | New | Eruvaka | New - Critical | Mech | rB |  | 1 | 2026-07-08 | [7 empty] | No | [11 empty] | 10
96 | 2026-07-07 | TBA | Cable from PCB doser connector to relay PCB | New | Eruvaka | New - Critical | HW | rB | A | 1 | 2026-07-08 |  | 0% | Yes |  |  |  |  | No | [11 empty] | 10
97 | 2026-07-07 | TBA | Inter connect cable from Relay PCB to PM PCB | New | Eruvaka | New - Critical | HW | rB | A | 1 | 2026-07-08 |  | 0% | Yes |  |  |  |  | No | [11 empty] | 10
98 | 2026-07-07 | ERC025 | Nylon cable Tags (100x2.2) - 5 No's for each controller | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 5 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
99 | 2026-07-07 | ERPA023 | Foam Sheets-Controller Box 650*665*10 | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 0.25 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
100 | 2026-07-07 | ERPA012 | Cartoon box controller box-660*650*410-7ply | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 0.125 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
101 | 2026-07-07 | ER825 | SQ125 Control Box Structure | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
102 | 2026-07-07 | ER087 | Battery 12V 42amp | Carryover | Eruvaka | Carryover - Regular | HW | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
103 | 2026-07-07 | ER795 | Battery Cover | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
104 | 2026-07-07 | ER787 | SQ125 Battery Lock Bracket | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 1 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
105 | 2026-07-07 | ER734 | Float Drums (RED) | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 4 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
106 | 2026-07-07 | ER050 | UV Black Cable Tag | Carryover | Eruvaka | Carryover - Regular | Mech | rB |  | 6 | 2026-07-08 | 2026-07-08 | 100% |  | 0 |  |  |  | Yes | [11 empty] | 10
XT-60 Male Connector
Relay PCB
Cable from PCB doser connector to relay PCB
Inter connect cable from Relay PCB to PM PCB
Formulas:
Status (Days) = IF(OR([Design Readiness Planned]="",[Design Readiness Actual]=""),"",SIGN([Design Readiness Actual]-[Design Readiness Planned])*(NETWORKDAYS(MIN([Design Readiness Planned],[Design Readiness Actual]),MAX([Design Readiness Planned],[Design Readiness Actual]))-1))
Status (Days) = IF(OR([Part Qualification Readiness]="",[PE Verif. Actual]=""),"",SIGN([PE Verif. Actual]-[Part Qualification Readiness])*(NETWORKDAYS(MIN([Part Qualification Readiness],[PE Verif. Actual]),MAX([Part Qualification Readiness],[PE Verif. Actual]))-1))
Vendors Identification Actual = [Lead time confirmation Actual]
Lead time confirmation Planned = IF(OR([Vendor Finalization ((ToCo,)]="",[Lead Time Type]=""),"",WORKDAY([Vendor Finalization ((ToCo,)],IF([Lead Time Type]="Low",30,IF([Lead Time Type]="Medium",45,IF([Lead Time Type]="High",60,"")))))

## RACI Matrix (hidden)
Department | Owner | Design Readiness | Part Qualification Readiness | Sourcing Readiness | Supplier Qualification | Sample / Lot Procurement | Factory Handover Readiness
Product Engineering | Mallesha | A | A | C | C | C | A
Design | Ravindra Namburi | R | C | C | C | C | R
HW | Pavan K | R | R | C | C | C | R
FW | Prem | R | C | I | I | I | R
Procurement | Ravindra Kolla | C | C | A/R | S | R | C
Quality | Jeyamurgan | C | A/R | I | R | C | A/R
Production | Venu | C | C | I | C | C | R
Customer Success | Pavan N | C | I | I | I | I | C
V&V | Kiran | C | R | I | C | C | R
R – Responsible ¦ A – Accountable¦ C – Consulted ¦ I – Informed
Note: | Example

## Timeline (hidden)
S.No | Readiness Stage | Key Activities / Deliverables | Responsible | Accountable | Planned Start | Target Date | Expected Completion | Actual Completion | Duration (Days) | Days Remaining | Schedule Status | Dependency | Remarks
1 | Design Readiness | Design freeze approval, final drawings, final BOM, specifications, design review closure | R&D | P&E |  | 2026-08-13 |  |  |  | -54 | Delayed
2 | Part Qualification Readiness | Part qualification plan, qualification requirements, identified qualification parts | Quality / V&V | P&E | 2026-07-07 | 2026-08-15 |  |  | 40 | -52 | Delayed
3 | Sourcing Readiness | Approved source list, sourcing confirmation, supplier lead time | SCM | P&E | 2026-07-31 | 2026-09-15 |  |  | 47 | -21 | Delayed
4 | Supplier Qualification | Supplier qualification report/approval, supplier evaluation closure | Quality / SCM | Quality | [6 empty] | Delayed
5 | Sample / Lot Procurement | Approved samples/lots received, incoming inspection/verification records | SCM | SCM | [6 empty] | Delayed
6 | Factory Handover Readiness | Final BOM, SOPs, qualification reports, production documents, KT and factory handover | P&E / Quality | P&E | [6 empty] | Delayed
| Note | Example
Formulas:
Days Remaining = IF([Expected Completion]<>"","",IF([Target Date]="","",[Target Date]-TODAY()))
Schedule Status = IF([Actual Completion]<>"","Completed",IF([Target Date]<TODAY(),"Delayed",IF([Target Date]-TODAY()<=7,"At Risk","On Track")))
Target Date = [Target Date, row above]+2